## Risk Register
Enterprise Risk Register — Q2 2026
NexusAI Pilot Client ¦ Digital Banking Division ¦ Review Date: June 24, 2026 ¦ Owner: Chief Risk Officer
Risk ID | Category | Risk Description | Likelihood (1-5) | Impact (1-5) | Inherent Score | Control Description | Control Effectiveness | Residual Score | Rating | Owner | Action / Deadline
R-001 | Operational | Payment success rate below 99% target due to middleware timeout bug in v2.4.1 patch | 4 | 4 | 16 | Engineering patch deployed to staging; root cause analysis complete; monitoring alerts active | PARTIAL | 14 | HIGH | CTO | Deploy fix to production by June 3, 2026
R-002 | Financial | Net interest margin declining for third consecutive quarter — 15.2% vs 18% target | 3 | 4 | 12 | Monthly P&L review; quarterly Board reporting; cost reduction programme initiated | EFFECTIVE | 8 | MEDIUM | CFO | Present margin recovery plan to Board by June 24
R-003 | Compliance | AML false positive rate at 23% exceeds 18% internal threshold and 20% regulator guidance | 3 | 3 | 9 | Monthly AML metrics review; escalation protocol to CCO; FIU notifications current | PARTIAL | 7 | MEDIUM | CCO | Initiate rule-set recalibration project by July 1, 2026
R-004 | Strategic | SAMA (Saudi Arabia) licensing application delayed — GCC revenue forecast at risk | 3 | 4 | 12 | Regular regulatory liaison; external legal counsel engaged; CEO oversight | PARTIAL | 10 | HIGH | CEO | Submit revised SAMA application by August 15, 2026
R-005 | Operational | Core banking middleware upgrade 6 weeks overdue — vendor delivery risk | 4 | 5 | 20 | Vendor management meetings weekly; contingency plan (rollback to v2.1) documented | PARTIAL | 18 | CRITICAL | CTO | Board approval for contingency plan June 24; hard deadline July 15
R-006 | Regulatory | Central Bank quarterly liquidity report due June 15 — data extraction not started | 4 | 5 | 20 | Regulatory calendar maintained; escalation to CFO triggered | INEFFECTIVE | 20 | CRITICAL | CFO | START DATA EXTRACTION IMMEDIATELY — deadline June 15
R-007 | Financial | KYC vendor contract 34% above market rate ($1.4M vs $1.0M market) | 3 | 3 | 9 | Contract review cycle; vendor comparison completed; renegotiation authority requested | PARTIAL | 7 | MEDIUM | COO | Execute renegotiation by June 30, 2026; savings $420K p.a.
R-008 | Compliance | Agent banking outlet KYC refresh 4 months overdue for 312 outlets | 3 | 4 | 12 | Remediation plan submitted to regulator; visit schedule being finalised | PARTIAL | 10 | HIGH | CCO | Complete high-risk outlets by July 31; full completion August 15
R-009 | Technology | Data warehouse uptime 98.1% vs 99.5% target — planned maintenance overrun | 2 | 2 | 4 | Incident management process; post-mortem scheduled; capacity review initiated | EFFECTIVE | 1 | LOW | CTO | Revised maintenance window June 8–9; uptime target to be restored
R-010 | Reputational | NPS score declining (54 to 51 in May) — below 50 triggers Board escalation | 3 | 3 | 9 | Monthly NPS tracking; customer experience taskforce active; complaint root cause analysis | PARTIAL | 7 | MEDIUM | COO | Resolve payment failure issue to prevent further NPS decline
R-011 | Compliance | 3 open regulatory queries from Q1 and April inspection (2 HIGH, 1 LOW finding) | 3 | 4 | 12 | Legal and compliance response team; documented response tracker; regulatory engagement | PARTIAL | 10 | HIGH | CCO | Finding 1 response due June 30; Finding 2 site visits June-July
R-012 | Strategic | SME banking proposition requires $2.1M investment — capital allocation decision needed | 2 | 3 | 6 | Board governance process; business case development in progress | EFFECTIVE | 2 | LOW | CEO | Full business case to Board September 2026
R-013 | Cyber | Third-party vendor security certification pending for middleware — extends attack surface | 3 | 4 | 12 | Vendor security review; additional monitoring controls deployed during delay | PARTIAL | 10 | HIGH | CISO | Obtain vendor certification confirmation by June 30
R-014 | Fraud | Payment failure incident increased fraud exposure window — 892 attempts in May | 3 | 3 | 9 | Real-time fraud monitoring; rules tightened post-incident; recovery rate 71% | EFFECTIVE | 5 | MEDIUM | CCO | Fraud rule refresh following payment fix deployment

## Summary
Risk Summary — Q2 2026
Rating | Count | % of Total | Trending | Key Action
CRITICAL | 0 | 0% | STABLE | N/A
HIGH | 6 | 43% | WORSENING | CEO/Board intervention required
MEDIUM | 6 | 43% | STABLE | Management monitoring
LOW | 2 | 14% | STABLE | Routine monitoring